## Switching checklist - moving to
Switching checklist - moving to new job software
Work top to bottom. Do not cancel the old system until the last row is done.
# | Phase | Task | Owner | Due | Done (Y/N) | Notes
1 | Before you sign | Export the customer list (name, address, phone, email, notes) to CSV from the old system or your spreadsheet
2 | Before you sign | Export open invoices and unpaid balances. Decide whether to finish them in the old system or re-enter them
3 | Before you sign | Export the price book / service list with your current prices
4 | Before you sign | Export job history if the new tool can import it (ask: what file format, and what's the field limit?)
5 | Before you sign | Get the new vendor's price in writing: plan, users, add-ons, card fees, contract length, cancellation
6 | Before you sign | Ask your bookkeeper/accountant how the QuickBooks sync should map (customers, items, tax, payments)
7 | Before you sign | Check the old system's cancellation terms and renewal date so you don't pay twice
8 | Set-up | Import customers, then spot-check 10 records (addresses, phone numbers, duplicates)
9 | Set-up | Load the price book and tax rates; build 3 quote templates you actually use
10 | Set-up | Connect QuickBooks during a test period first; confirm one invoice and one payment sync correctly
11 | Set-up | Set up users and permissions (office vs. field) and install the app on every tech's phone
12 | Set-up | Turn on payments; run one small test charge and refund
13 | Set-up | Set customer notifications (reminders, on-my-way texts) and read every template before it goes live
14 | Go-live | Run old and new side by side for 1-2 weeks on new jobs only
15 | Go-live | Train techs: clock in/out, job notes, photos, collecting payment
16 | Go-live | After 30 days: compare invoices sent and paid against the old way; fix any sync mismatches
17 | Go-live | Cancel the old system only after the final export is saved somewhere you control
LedgerAsk free template · by Mike, a Fayette County guy with a construction background · not tax or legal advice